## Sheet1
procuring entity | package | issue | description | commitment | steps taken | challenges | mitigation measures | way forward | concern type | sub-project
Temeke | Package 2 & 3 | Noise and vibration abatement | The source of noise and vibration in this project: heavy trucks, batch plant, machines (welding machines, excavator machine producing electricity and wheel loader) | High-intensity impact noise and vibration were dedicated to daytime | complied | No associated impact were raised during this month. | n/a | n/a | environmental | CHANG’OMBE ROAD (9 m width and 1.9 km length)
Temeke | Package 2 & 3 | Noise and vibration abatement | The source of noise and vibration in this project: heavy trucks, batch plant, machines (welding machines, excavator machine producing electricity and wheel loader) | Continuous maintenance of machines | complied | No associated impact were raised during this month. | n/a | n/a | environmental | TEMEKE-MBAGALA ROAD (9 m width and 3.5 km length)
Temeke | Package 2 & 3 | Noise and vibration abatement | The source of noise and vibration in this project: heavy trucks, batch plant, machines (welding machines, excavator machine producing electricity and wheel loader) | Protection of machine moving parts. | complied | No associated impact were raised during this month. | n/a | n/a | environmental | MCHICHA ROAD (7 & 9 m width and 1.89 km length)
Temeke | Package 2 & 3 | Noise and vibration abatement | The source of noise and vibration in this project: heavy trucks, batch plant, machines (welding machines, excavator machine producing electricity and wheel loader) | Provision of Ear maffs | complied | No associated impact were raised during this month. | n/a | n/a | environmental | CHANG’OMBE ROAD (9 m width and 1.9 km length)
Temeke | Package 2 & 3 | Employment |  | About 148 Labours have been employed. | All employees provided with employment contracts. | No cases among labours | n/a | n/a | social | MCHICHA ROAD (7 & 9 m width and 1.89 km length)
Temeke | Package 2 & 3 | Community Meetings and Consultations |  | Community consultation is ongoing on daily basis | Complied. Reported cases from the community handled as per occurrence | none | n/a | n/a | social | CHANG’OMBE ROAD (9 m width and 1.9 km length)
Temeke | Package 2 & 3 | Welfare Facilities | Drinking water toilets and washrooms that employees use when they are work | Drinking water, toilets and washrooms are well provided | The contractor have been reminded to improve this facilities | none |  | n/a | social | MCHICHA ROAD (7 & 9 m width and 1.89 km length)
Temeke | Package 2 & 3 | GBV | Issues related to gender based violence | Gender based violence is part of the project implementation e.g prevention of Sexual abuse, child labour e.t.c. | No reported cases so far | n/a | n/a | n/a | social | TEMEKE-MBAGALA ROAD (9 m width and 3.5 km length)
Temeke | Package 2 & 3 | Employment |  | About 204 Labours have been employed. | All labour conditions observed. No case has been reported. |  |  |  | social | TEMEKE-MBAGALA ROAD (9 m width and 3.5 km length)
Temeke | Package 1 | Safety and health management plan |  | Health and Safety Management Plan implementation. | Approved | none |  |  | healthy and safety | Mwanamtoti road (1.8 km length)
Temeke | Package 1 | PPE |  | PPE – Helmet, gloves, reflective jackets, gumboots/safety shoes | PPE are issued to workers as required |  |  |  | healthy and safety | Mwanamtoti road (1.8 km length)
Temeke | Package 1 | Safety trainings |  | EHS awareness trainings | Trainings are ensured as per requirements. |  |  |  | healthy and safety | Mwanamtoti road (1.8 km length)
Temeke | Package 1 | Traffic safety |  | Traffic reflective signage, flag persons, barricades are provided | Daily monitoring implemented. |  |  |  | healthy and safety | Mwanamtoti road (1.8 km length)